# PROJECT NOTES — HOLLOWAY RE TREATY ACCOUNT

Week of June 30, 2026

Owner: R. Vega

This week:

S. Okafor delivered the Holloway Re aggregate analysis — the test shows a technical breach on the ceded aggregate (4.3x actual vs 4.0x expected loss-ratio limit)

R. Vega reviewed the analysis and confirmed the breach is real; not material at this stage but must be reported

Underwriting committee briefing scheduled for Tuesday July 2; R. Vega presenting

Cedent call with Holloway Re's Chief Actuary booked for July 7 to discuss the remediation plan

Legal reviewed the aggregate definition — the ratio is calculated on a trailing-12-month basis, which works slightly in Holloway's favor; final number is 4.1x after adjustment

Legacy reporting migration completed Friday (on schedule); Holloway Re treaty data now live in the new schema

Upcoming:

Underwriting committee briefing July 2 (R. Vega presenting the aggregate exception and remediation options)

Cedent call July 7 (P. Chen and R. Vega attending)

Holloway Re to submit a remediation plan letter by July 14 per the treaty agreement

Monitoring cycle continues weekly until remediation is confirmed

Open issues:

Holloway Re has not yet responded to the remediation-plan timeline request sent June 28

One data discrepancy in the legacy migration for the Q1 aggregate test — IT investigating, expected resolution July 3